## Sheet1
Colors for status column | No. | Category of Work | Task | Hours per Week | Deliverable | Start | End | Status | Notes
Planned | 1 | Encoding and Proofing | Encoding and proofing of the Missionary Travels m.s. vol. 3 (Additional Hours) |  | Encoding and proofing of Missionary Travels m.s. vol. 3, as assigned, completed in full | 2016-10-01 | 2016-11-30
In-Progress | 2 | Encoding and Proofing | Encoding of the published version of Missionary Travels |  | Encoding of published version of Missionary Travels completed in full | 2016-10-01 | 2016-11-30
Finised | 3 | Zambezi Grant | Research possible grant options for Zambezi project. Identify funding agencies permitting collaboration between USA and UK institutions. Identify particular funding themes/calls relevant to the project. |  | Short list of funding agencies permitting collaboration between USA and UK institutions. Identify particular funding themes/calls relevant to the project. | 2016-10-17 | 2016-11-14
Behind Schedule | 4 | Research Essays | Identify independent essay topic #1. Identify possible essay topics #2 and #3. |  | Essay topic #1 confirmed. Possible essay topics #2 and #3 identified. | 2016-10-17 | 2016-10-31
| 5 | Presentations | Develop 10 minute presentation outlining objectives and results for LEAP event at QUB, Friday 18th November, 4pm |  | 10 minute presentation outlining objectives and results of first phase of Livingstone Spectral Imaging Project (talk and slides) | 2016-10-17 | 2016-11-18
6
| 7 | Research Essays | Research and draft first independent essay |  | Draft of first essay delivered | 2016-11-01 | 2017-01-31
| 8 | Encoding and Proofing | Training in extracting and reviewing TEI data from Missionary Travels (during AW's visit to QUB) |  | Proficiency in extracting and reviewing TEI data from Missionary Travels | 2016-11-18 | 2016-11-23
| 9 | XSLT/Drupal | Training in XSLT and Drupal (during AW's visit to QUB) |  | Contributions to XSLT for Final Field Diaries Project. All introductions to Final Field Diaries project converted to Drupal. | 2016-11-18 | 2016-11-23
| 10 | Encoding and Proofing | Contribute to final review of transcription data by reviewing and correcting as needed all extracted lists of marked TEI data |  | All extracted lists of marked TEI data corrected and reconciled | 2016-11-24 | 2017-02-28
11
| 12 | Annotated Lists | Develop and annotate list of Livingstone Online resources complementary to critical edition (i.e. maps from the expedition; marked up proof illustrations; John Murray's copybooks/ledgers; relevant letters) |  | Annotated list of Livingstone Online resources complementary to critical edition | 2016-12-01 | 2016-12-31
| 13 | Annotated Lists | Locate and annotate illustrative material for editorial introduction and associated essays |  | List of 20 relevant images (i.e. heavily edited up m.s. pages; marked up proof illustrations; portraits; maps; paintings; photographs of objects in LO archive) | 2016-12-01 | 2016-12-31
| 14 | Presentations | Prepare and submit abstract for up to three national or international conference (BAVS or similar) |  | Abstract written and submitted for up to three conferences | 2017-12-01 | 2017-12-31
15
| 16 | Presentations | Develop 15 minute presentation for trip to University of Nebraska-Lincoln and Oberlin College (date of trip tbc) |  | 15 minute presentation outlining objectives and to-date results of Missionary Travels project (talk and slides) | 2017-01-01 | 2017-02-28
| 17 | XSLT/Drupal | Training in XSLT and Drupal (during JL/KS's visit to UNL) |  | Contributions to XSLT for Missionary Travels Project. Encode one or more Missionary Travels sample essays in Drupal. | 2017-01-01 | 2017-02-28 |  | a
| 18 | Zambezi Grant | Participate in developing Zambezi Expedition grant application |  | Written contributions and revisions to draft of Zambesi Expedition grant narrative. Role in Zambesi Expedition grant defined and articulated in grant narrative. | 2017-01-01 | 2017-05-31
19
| 20 | Critical Notes | Contribute to writing critical notes (secondary task) |  | All assigned critical notes completed | 2017-02-01 | 2017-04-30
| 21 | Research Essays | Develop feedback on first draft of essay (JL/AW) |  | Feedback on draft of first essay delivered | 2017-02-01 | 2017-02-14
| 22 | Research Essays | Identify independent essay topic #2 |  | Essay topic #2 confirmed | 2017-02-01 | 2017-02-14 |  | Need a three-way meeting to confirm this. Topic has to suit Kate's interest but also contribute to Livingstone Online needs.
| 23 | Research Essays | Revised first essay based on feedback |  | Revised version of first essay completed | 2017-02-14 | 2017-02-28
| 24 | XSLT | Revising XSLT for Missionary Travels |  | Final version of XSLT for Missionary Travels | 2017-02-01 | 2017-02-28
25
| 26 | Research Essays | Complete and submit first independent essay for peer review and publication on Livingstone Online |  | First essay submitted to LO for peer review | 2017-03-01 | 2017-03-01
| 27 | Research Essays | Research and draft second independent essay |  | Draft of second essay delivered | 2017-03-01 | 2017-05-31
28
| 29 | Critical Notes | Add critical notes (xml:id) to XML files |  | All xml:id's added to transcriptions | 2017-04-01 | 2017-04-30
30
| 31 | Presentations | Develop paper and slides for conference in the spring or summer. Paper will be based on in-progress critical essay for Livingstone Online. |  | 20 minute paper and slides for conference | 2017-05-01 | 2017-08-31
32
| 33 | Research Essays | Develop feedback on second draft of essay (JL/AW) |  | Feedback on draft of second essay delivered | 2017-06-01 | 2017-06-14
| 34 | Research Essays | Identify independent essay topic #3 |  | Essay topic #3 confirmed | 2017-06-01 | 2017-06-30 |  | Need a three-way meeting to confirm this. Topic has to suit Kate's interest but also contribute to Livingstone Online needs.
| 35 | Research Essays | Revised second essay based on feedback |  | Revised version of second essay completed | 2017-06-14 | 2017-06-30
36
| 37 | Research Essays | Complete and submit second independent essay for peer review and publication on Livingstone Online |  | Second essay submitted to LO for peer review | 2017-07-01 | 2017-07-01
38
| 39 | Outreach | Develop school outreach sheets on Missionary Travels |  | Outreach sheets should be in line with those currently available on Livingstone Online | 2017-07-01 | 2017-08-31
| 40 | Research Essays | Research and draft third independent essay |  | Draft of third essay delivered | 2017-07-01 | 2017-08-31
41
| 42 | Research Essays | Develop feedback on third draft of essay (JL/AW) |  | Feedback on draft of third essay delivered | 2017-09-01 | 2017-09-14
| 43 | Presentations | Develop 15 minute presentation at launch of digital edition (NLS or QUB, date TBC) |  | 15 minute presentation outlining objectives and results of Missionary Travels project (talk and slides) | 2017-09-01 | 2017-09-30
| 44 | Research Essays | Revised third essay based on feedback |  | Revised version of third essay completed | 2017-09-14 | 2017-09-30
| 45 | Research Essays | Complete and submit third independent essay for peer review and publication on Livingstone Online |  | Third essay submitted to LO for peer review | 2017-10-01 | 2017-10-01