## Sheet1
Item | Status | End | People | Notes
Critical Essays - Drafting
Digital Humanities, Exploration Literature, and Missionary Travels |  | 2017-09-19 | JL
Textual Principles and Encoding Practices |  | 2017-12-07 | JL
The Missionary Travels Manuscript: An Overview |  | 2018-03-05 | JL
The Journey to Print: Composition and Publication Process |  | 2018-03-05 | JL
Manuscript Analysis |  | 2018-05-30 | JL
Introduction to Edition |  | 2018-06-15 | JL
Critical Essays - Review
Digital Humanities, Exploration Literature, and Missionary Travels |  | 2017-10-15 | AW
Digital Humanities, Exploration Literature, and Missionary Travels (Revisions) |  | 2017-03-12 | JL
Textual Principles and Encoding Practices |  | 2018-02-22 | AW
Textual Principles and Encoding Practices (Revisions) |  | 2018-04-30 | JL
The Missionary Travels Manuscript: An Overview |  | 2018-03-27 | JM
The Missionary Travels Manuscript: An Overview (Revisions) |  | 2018-05-30 | JL
The Journey to Print: Composition and Publication Process |  | 2018-03-27 | JM
The Journey to Print: Composition and Publication Process (Revisions) |  | 2018-05-30 | JL
Manuscript Analysis |  | 2018-06-30 | JM
Manuscript Analysis (Revisions) |  | 2018-07-30 | JL
Introduction to Edition |  | 2018-07-15 | AW
Introduction to Edition (Revisions) |  | 2018-07-30 | JL
Transcription Data
Create Github tickets for outstanding XSLT work |  | 2017-10-01 | JL
Complete XSLT Github tickets |  | 2017-10-15 | AW
Deliver final transcriptions |  | 2017-10-15 | JL
Review of completed final transcriptions |  | 2017-11-01 | AW
Deliver additional transcriptions |  | 2017-11-08 | JL/KS
Build images & transcriptions |  | 2017-11-09 | AW | Done; we need to resolve the <anchor> issue
Develop MT multitext viewer |  | 2017-11-09 | NB
Review of additional transcription fragments |  | 2017-11-11 | AW
Final Additional transcription fragments (revisions) |  | 2017-11-11 | JL | not needed
Final transcription (revisions) (including definition files, xslt and css) |  | 2017-11-14 | JL
Supporting Development
Get critical materials into Drupal |  | early Dec-18 | JL | AW will train; needs to be done before adding illustrations
Initial Bibliography |  | 2018-12-20 | JL/AW
Edition Guide |  | 2018-12-20 | JL/AW
Project Team |  | 2018-12-20 | JL/AW
Acknowledgments |  | 2018-12-20 | JL/AW
Release beta edition |  | 2019-01-01 | JL/AW
First Edition Tasks
Completed glossary |  |  | JL
Integrate glossary updates into XML |  |  | JL/KS
Key Terms in MT |  |  | JL
Project History |  |  | JL/AW
Project Documentation |  |  | AW/JL | One packet with highlights
Final Bibliography |  |  | JL
Add illustrations to critical materials and elsewhere |  |  | JL/AW | Non-trivial task; will take a good chunk of time
Release first edition |  | 2019-04-01 | JL/AW