## Sect 01-09
I: Transcription and Encoding
| Sect 01 | Sect 02 | Sect 03 | Sect 04 | Sect 05 | Sect 06 | Sect 07 | Sect 08 | Sect 09
Deadline | 21st May 2014 | 1st July 2014 | 1st July 2014 | 1st Sept 2014 | 1st Sept 2014 | 11th Sept 2014 | 16th Sept 2014 | 3rd Oct 2014 | 21st Nov 2014
Kate | bar: Sect 01; Sect 03 to Sect 04; Sect 07 to Sect 08
Johanna | bar: Sect 01 to Sect 02; Sect 05 to Sect 06
Peter | bar: Sect 09
Stephen
Justin | bar: Sect 01
II: Proofing
| Sect 01 | Sect 02 | Sect 03 | Sect 04 | Sect 05 | Sect 06 | Sect 07 | Sect 08 | Sect 09
Deadline | 9th June 2014 | 4th Aug 2014 | 4th Aug | 17th Sept 2014 | 21st Nov | 22nd Sept | 29th Sept 2014 | 21st Nov 2014 | 9th Feb
Kate | bar: Sect 01 to Sect 02; Sect 05 to Sect 06; Sect 09
Johanna | bar: Sect 01; Sect 03 to Sect 04; Sect 07 to Sect 08
Peter
Stephen
Justin | bar: Sect 01
III: Review
| Sect 01 | Sect 02 | Sect 03 | Sect 04 | Sect 05 | Sect 06 | Sect 07 | Sect 08 | Sect 09
Justin

## Sect 10-17
I: Transcription and Encoding
| Sect 10 | Sect 11 | Sect 12 | Sect 13 | Sect 14 | Sect 15 | Sect 16 | Sect 17
Deadline | 16th December | 16th December | 7th January | 19th January | 6th February | 20th Feb | 25th Feb | 18th March
Kate | bar: Sect 10; Sect 13; Sect 16
Johanna | bar: Sect 11
Peter | bar: Sect 14; Sect 17
Stephen | bar: Sect 12; Sect 15
Justin
II: Proofing
| Sect 10 | Sect 11 | Sect 12 | Sect 13 | Sect 14 | Sect 15 | Sect 16 | Sect 17
Deadline | 18th Feb | 11th May | 26th March | 26th March | 18th May | 26th March | 5th June | 12th June
Kate | bar: Sect 11 to Sect 12; Sect 14 to Sect 15
Johanna
Peter
Stephen | bar: Sect 10; Sect 13; Sect 16 to Sect 17
Justin
III: Review
| Sect 10 | Sect 11 | Sect 12 | Sect 13 | Sect 14 | Sect 15 | Sect 16 | Sect 17
Justin

## Sect 18-25
I: Transcription and Encoding
| Sect 18 | Sect 19 | Sect 20 | Sect 21 | Sect 22 | Sect 23 | Sect 24 | Sect 25
Deadline | 26th March | 7th April | 17th April | 23rd April | 30th April | 13th May | 17th Feb | 10th July
Kate | bar: Sect 24
Johanna
Peter | bar: Sect 19 to Sect 20; Sect 22; Sect 25
Stephen | bar: Sect 18; Sect 21; Sect 23
Justin
II: Proofing
| Sect 18 | Sect 19 | Sect 20 | Sect 21 | Sect 22 | Sect 23 | Sect 24 | Sect 25
Deadline | 12th June | 24th June | 1st July | 21st July | 1st July | 10th Feb | 31st March
Kate | bar: Sect 22; Sect 25
Johanna
Peter | bar: Sect 18; Sect 21; Sect 23
Stephen | bar: Sect 19 to Sect 20; Sect 24
Justin
III: Review
| Sect 18 | Sect 19 | Sect 20 | Sect 21 | Sect 22 | Sect 23 | Sect 24 | Sect 25
Justin

## Sect 26-33
I: Transcription and Encoding
| Sect 26 | Sect 27 | Sect 28 | Sect 29 | Sect 30 | Sect 31 | Sect 32 | Sect 33
Deadline | 8th August | 8th March | 27th Jan | 17th July | 31st July | 31st July | 17th August | 3rd September
Kate | bar: Sect 26
Johanna
Peter | bar: Sect 30
Stephen | bar: Sect 27 to Sect 29; Sect 31 to Sect 33
Justin
II: Proofing
| Sect 26 | Sect 27 | Sect 28 | Sect 29 | Sect 30 | Sect 31 | Sect 32 | Sect 33
Deadline | Sect 26: 17th May; Sect 30: 14th April; Sect 31: 13th Feb
Kate | bar: Sect 29; Sect 31 to Sect 33
Johanna
Peter
Stephen | bar: Sect 26; Sect 30
Justin | bar: Sect 27 to Sect 28
III: Review
| Sect 26 | Sect 27 | Sect 28 | Sect 29 | Sect 30 | Sect 31 | Sect 32 | Sect 33
Justin

## Sect 34-43
I: Transcription and Encoding
| Sect 34 | Sect 35 | Sect 36 | Sect 37 | Sect 38 | Sect 39 | Sect 41 | Sect 43
Deadline | 1st Jan | 12th Jan | 8th July |  | 20th July | 20th July | 10th Aug | 24th Aug
Kate | Sect 37: Transcribed at DH Summer School
Johanna
Peter
Stephen | bar: Sect 34 to Sect 36; Sect 38; Sect 41 to Sect 43
Justin
II: Proofing
| Sect 34 | Sect 35 | Sect 36 | Sect 37 | Sect 38 | Sect 39 | Sect 41 | Sect 43
Deadline |  |  | 17th Aug |  | 17th Aug | 5th Sept | 2nd Dec | 2nd Dec
Kate | bar: Sect 34; Sect 36 to Sect 38; Sect 41 to Sect 43
Johanna
Peter
Stephen | bar: Sect 39
Justin | bar: Sect 35
III: Review
| Sect 34 | Sect 35 | Sect 36 | Sect 37 | Sect 38 | Sect 39 | Sect 41 | Sect 43
Justin

## Sect 44-Final Pages
I: Transcription and Encoding
| Sect 44 | Sect 47 | Sect 48 | Sect Final Pages
Deadline | 31st Aug | 26th Sept | 31st October | 2nd December
Kate
Johanna
Peter
Stephen
Justin
II: Proofing
| Sect 44 | Sect 47 | Sect 48 | Sect Final Pages
Deadline | 16th Dec
Kate
Johanna
Peter
Stephen
Justin
III: Review
| Sect 44 | Sect 47 | Sect 48 | Sect Final Pages
Justin