## Sheet1
Category of Work | Task | Deliverable | Start | End | Status | Notes | Colors for status column
Zambezi Grant | Research possible grant options for Zambezi project. Identify funding agencies permitting collaboration between USA and UK institutions. Identify particular funding themes/calls relevant to the project. | Short list of funding agencies permitting collaboration between USA and UK institutions. Identify particular funding themes/calls relevant to the project. | 2016-10-17 | 2016-11-14 |  |  | Planned
Research Essays | Identify independent essay topic #1. Identify possible essay topics #2 and #3. | Essay topic #1 confirmed. Possible essay topics #2 and #3 identified. | 2016-10-17 | 2016-10-31 |  |  | In-Progress
Presentations | Write/submit abstract for 'Archives and Traces of the Past' conference | Submit abstract to 'Archives and Traces of the Past' conference | 2016-10-31 | 2016-11-02 |  |  | Finished
Presentations | Develop 10 minute presentation outlining objectives and results for LEAP event at QUB, Friday 18th November, 4pm | 10 minute presentation outlining objectives and results of first phase of Livingstone Spectral Imaging Project (talk and slides) | 2016-10-17 | 2016-11-18 |  |  | Behind Schedule
Training | Code Academy courses in HTML and CSS | Complete both Code Academy courses | 2016-10-31 | 2016-11-18
Encoding and Proofing | Training in extracting and reviewing TEI data from Missionary Travels (during AW's visit to QUB) | Proficiency in extracting and reviewing TEI data from Missionary Travels | 2016-11-18 | 2016-11-23
XSLT/Drupal | Training in XSLT and Drupal (during AW's visit to QUB) | Contributions to XSLT for Final Field Diaries Project. All introductions to Final Field Diaries project converted to Drupal. | 2016-11-18 | 2016-11-23
Research Essays | Establish high-level ideas on essay topic #1: 'Reading Livingstone in the Digital Age' | Meet to discuss preliminary research ideas on Livingstone's manuscripts | 2016-11-01 | 2016-12-19
Encoding and Proofing | Encoding and proofing of the Missionary Travels m.s. vol. 3 (Additional Hours) | Encoding and proofing of Missionary Travels m.s. vol. 3, as assigned, completed in full | 2016-10-01 | 2016-12-31
Annotated Lists | Develop and annotate list of Livingstone Online resources complementary to critical edition (i.e. maps from the expedition; marked up proof illustrations; John Murray's copybooks/ledgers) | Annotated list of Livingstone Online resources complementary to critical edition | 2017-01-01 | 2017-01-31
Encoding and Proofing | Encoding of the published version of Missionary Travels | Encoding of published version of Missionary Travels completed in full | 2016-10-01 | 2016-12-31
Research Essays | Research and draft first independent essay | Draft of first essay delivered | 2017-01-01 | 2017-02-28
Presentations | Prepare and submit abstract to BAVS | Abstract written and submitted to BAVS | 2017-01-01 | 2017-02-28 |  | Decided against submission
Presentations | Prepare and submit abstract for Africa and the Archive conference | Abstract written and submitted | 2017-03-20 | 2017-04-21 |  | Decided against submission
Presentations | Develop 15 minute presentation for trip to University of Nebraska-Lincoln and Oberlin College (date of trip tbc) | 15 minute presentation outlining objectives and to-date results of Missionary Travels project (talk and slides) | 2017-02-01 | 2017-02-28
Annotated Lists | Locate and annotate illustrative material for editorial introduction and associated essays | List of 20 relevant images (i.e. heavily edited up m.s. pages; marked up proof illustrations; portraits; maps; paintings; photographs of objects in LO archive) | 2017-02-01 | 2017-02-28
Research Essays | Develop feedback on first draft of essay (JL/AW) | Feedback on draft of first essay delivered | 2017-02-01 | 2017-02-14
Research Essays | Revised first essay based on feedback | Revised version of first essay completed | 2017-02-14 | 2017-04-30
Encoding and Proofing | Contribute to final review of transcription data by reviewing and correcting as needed all extracted lists of marked TEI data | Initial review of lists | 2017-05-02 | 2017-05-08
Research Essays | Complete and submit first independent essay for peer review and publication on Livingstone Online | First essay submitted to LO for peer review | 2017-05-08 | 2017-05-31
Research Essays | Identify independent essay topic #2 | Essay topic #2 confirmed | 2017-05-02 | 2017-05-31 |  | Need a three-way meeting to confirm this. Topic has to suit Kate's interest but also contribute to Livingstone Online needs. --We'll discuss when I'm in the UK (AW).
Zambezi Grant | Participate in developing Zambezi Expedition grant application | Written contributions and revisions to draft of Zambesi Expedition grant narrative. Role in Zambesi Expedition grant defined and articulated in grant narrative. | 2017-01-01 | 2017-07-01
Critical Notes | Add critical notes (xml:id) to XML files | All xml:id's added to transcriptions | 2017-05-08 | 2017-06-30 |  | All critical notes that have been written have been added to transcriptions (people, orgName, settlement, region).
Presentations | Prepare and submit abstract to DH conference | Abstract written and submitted to DH conference | 2017-05-01 | 2017-05-31 |  | Decided Kate had attended and presented at enough conferences. Did TEI workshop instead.
Research Essays | Respond to reader's report and revise first research essay | Respond to reader's report and revise first research essay | 2017-08-07 | 2017-09-01
Encoding and Proofing | Contribute to final review of transcription data by reviewing and correcting as needed all extracted lists of marked TEI data | Integrate corrections into XML | 2017-05-08 | 2017-09-06
Presentations | Develop paper and slides for conference in the spring or summer. Paper will be based on in-progress critical essay for Livingstone Online. | 20 minute paper and slides for conference | 2017-05-01 | 2017-08-31 |  | Presentation delivered at U. Edinburgh in Geography Department.
Encoding of the published version of Missionary Travels | Adding images to published version of MT | Add all images to published MT xml file | 2017-08-11 | 2017-10-01
Outreach | Develop school outreach sheets on Missionary Travels | Outreach sheets should be in line with those currently available on Livingstone Online | 2017-07-01 | 2017-10-01
Dissemination | Meeting to discuss MT social media dissemination strategies | Notes from meetings; these will guide our dissemination efforts going forward. Kate provides any relevant documentation. | 2017-10-01 | 2017-10-01
Research Essays | Publish essay one on Livingstone Online | Encode essay in Drupal and add illustrations | 2017-09-01 | 2017-10-01
Outreach/Dissemination | Contribution to blog | Write blog post on MHRA fellowship year | 2017-08-20 | 2017-10-01
Research Essays | Research and draft second independent essay | Draft of second essay delivered | 2017-10-01 | 2018-03-01 | Will happen post-grant.
XSLT/Drupal | Additional training in Drupal | Participate in developing Drupal interface for Missionary Travels | 2018-02-01 | 2018-04-30 | Will happen post-grant.
Research Essays | Develop feedback on draft of second essay (JL/AW) | Feedback on draft of second essay delivered | 2018-03-01 | 2017-03-15 | Will happen post-grant.
Research Essays | Revise second essay based on feedback. Complete and submit second for peer review and publication on Livingstone Online | Second essay revised and submitted to LO for peer review | 2018-03-15 | 2017-04-15 | Will happen post-grant.
Presentations | Develop 15 minute presentation at launch of digital edition (NLS or QUB, date TBC) | 15 minute presentation outlining objectives and results of Missionary Travels project (talk and slides) | TBC | TBC | Will happen post-grant.