## Sheet1
Item | Status | End | People | Notes
Critical Essays - Drafting
Editorial Statement |  |  | JL
Manuscript Structure and Composition |  |  | JL
Publishing MT in 1857 |  |  | JL
Introduction to Edition |  |  | JL
Critical Essays - Review
Editorial Statement |  |  | AW | 2 weeks to implement suggested revisions
Manuscript Structure and Composition |  |  | AW | 2 weeks to implement suggested revisions
Publishing MT in 1857 |  |  | AW | 2 weeks to implement suggested revisions
Introduction to Edition |  |  | AW | 3 days to implement suggested revisions
Transcription Data
Deliver final transcriptions |  |  | JL
Create Github tickets for outstanding XSLT work |  |  | JL
Review of completed final transcriptions |  |  | AW | 1 week to implement suggested revisions
Complete XSLT Github tickets |  |  | AW
Build images & transcriptions and two versions of text pages |  |  | AW
Supporting Materials
Supporting Illustrations Page |  |  | JL/AW | First priority in supporting materials
Bibliography |  |  | JL/AW | Second priority of supporting materials
Edition Guide |  |  | JL/AW
Project Team |  |  | JL/AW
Acknowledgments |  |  | JL/AW
Additional Tasks
Get critical materials into Drupal |  |  | JL | AW will train; needs to be done before adding illustrations
Add illustrations to critical materials and elsewhere |  |  | JL/AW | Non-trivial task; will take a good chunk of time
Release beta edition |  |  | JL/AW
First Edition Tasks
Afterlives of MT |  |  |  | Critical Essay
Reading MT Today |  |  |  | Critical Essay
Completed glossary
Key Terms in MT
Project History
Project Documentation |  |  |  | One packet with highlights
Illustration of new materials